## Run Sheet
TIME | TASK | SUPPLIER INVOLVED | ADDITIONAL NOTES | TIME | BERNICE - MAKEUP | JESS - HAIR
|  |  |  | 8:30am | Hair & makeup artists arrive on-site
8:30am | Hair & makeup artists arrive on-site | Bernice Mansfield | Refer to HMU timeline for breakdown --> | 9:00am | MOG - Romani | Bridesmaid #1 - Rebecca
9:00am | Breakfast to be delivered to the suite for bride and party | Brides Who Brunch |  | 9:30am | SIL - Kathleen
9:00am | Hair & makeup commence for bridal party and MOB/MOG/SIL |  |  | 9:45am |  | MOG - Romani
12:00pm | Bride - Emily (H) |  |  | 10:00am | Bridesmaid #1 - Rebecca
12:45pm | Bride - Emily (MU) |  |  | 10:30am | Bridesmaid #2 - Steph | SIL - Kathleen
1:00pm | Florist, Cathy drops off bouquets & boutonnieres to bride & groom suites before setting up ceremony & reception | Twig & Hynes |  | 11:00am | Bridesmaid #3 - Elise
1:30pm | Photographers arrive and visit groom & co in grooms suite first | Lou Lou Memphis |  | 11:15am |  | Bridesmaid #2 - Steph
2:15pm | H&MU pack down | Bernice Mansfield |  | 11:30am | MOB - Mary-Ann
2.30pm | Photographers arrive at Brides suite | Lou Lou Memphis |  | 12:00pm | Bride - Emily (H) | Bridesmaid #3 - Elise
2.00pm | Videographer arrives - Visits groom suite - for 30 minutes | Moon & Back Co |  | 12:45pm | Bride - Emily (MU) | Cousin - Maddy
2.30pm | Videographer arrive at Brides suite - for 1 hour | Moon & Back Co |  | 1:30pm | Cousin - Maddy | MOB - Mary-Ann
2.30pm | Celebrant, Kirby arrives to setup | Kirby Steele |  | 2:15pm | H&MU Pack Down
3:00pm | Kirby visits the bride in the suite, then will meet with the groom at 3.30pm at the riverdeck | Kirby Steele
3:15pm | Renee & Jamie arrive at Mitchelton to setup for ceremony | Tobi Tobi
3:30pm | Groom & groomsman to walk from hotel room – They will welcome guests as they arrive
3:30pm | Guests to arrive (via bus/individual transfers) to RIVER DECK (Mineral water offered on arrival)
3:45pm | Tobi Tobi begin pre- ceremony music | Tobi Tobi
3:55pm | Bride & bridesmaids to walk from hotel room
4:00pm | Ceremony to commence
4:30pm | Ceremony to conclude + immediate family photos to commence next to the riverdeck
4:30pm | 7Hr Beverage Package to begin + canapes served on the grassed area behind the river deck with Airstream Bar.
4:40pm | Tobi Tobi commence 1of2 20 minute sets | Tobi Tobi
4.45pm | Bridal party to depart for photos (2 golf buggy’s to be available + Bridal drinks/canapes for 7 people) |  | Please include non-alcoholic for pregnant bridesmaid.
5:10pm | Tob Tobi commence 2of2 20 minute sets | Tobi Tobi
5:30pm | Guests to be ushered to MONTAGE ROOM for reception | Tim Judd
6:00pm | Guests to be seated
6:10pm | MC to welcome guests + housekeeping | Tim Judd
6:15pm | MC to introduce bridal party | Tim Judd
6:25pm | First set of speeches – Mother/Father of the Bride + Father of the Groom | Mary-Ann/NIck & Richard
6:45pm | Entree served (30 minutes required) – Entertainment will perform dinner music | Paris & Co
7:15pm | Entree cleared
7:20pm | Second set of speeches - Best Man + Bridesmaid | David & Steph
7.35pm | Cutting of the cake & bridal first dance, followed by dance bracket (get people up early) | Paris & Co
8:00pm | Mains served (45 minutes required) - Entertainment will perform dinner music | Paris & Co
8:45pm | Mains cleared
9:00pm | Bride + Groom speech (Paris to take over Tim MC from here) | Emily & Patrick
9:10pm | Dance floor opens again | Paris & Co
9:40pm | Plated desserts to be served (30 minutes required) - Tea & coffee to be available
10:10pm | Desserts to be cleared, if applicable
10:30pm | Cake, tea + coffee to be offered
11:15pm | Bouquet throw
11:30pm | Bride + groom to depart (to hotel room)
11:30pm | 7 Hr beverage package to conclude - Event to conclude - Guests to make their way home
11:45pm | Local buses to depart with guests staying within Nagambie surrounds | Comi's Bus Lines